## Defect Logs for DemoBlaze E-com
Defect Logs for DemoBlaze E-commerce Platform
Defect ID | Defect Title | Description | Severity | Priority | Status | Steps to Reproduce | Detected Date | Assigned To
DEF_001 | No Validation for Payment Fields | System accepts invalid payment details (e.g., numbers in name, letters in card number, invalid date) without error. | High | High | Open | 1. Add product to cart. | 2025-07-01 | Rawan Ellsayed
2. Click "Cart" > "Place Order."
3. Enter Name: 123, Card: abc, Date: 1/6/2025.
4. Click "Purchase."
DEF_002 | Inaccurate Cart Interface Description | Acceptance criteria refers to a "cart icon" that does not exist; "Cart" link in Navbar used instead. | Medium | Medium | Open | 1. Review User Story 2 documentation. | 2025-07-01 | Rawan Ellsayed
2. Observe Navbar for "Cart" link.